## Plan
RIP Plan | Date | Exit Criteria | Outcome | Efforts (in Person Hours) | Assumptions | Progress | Date of Completion
Phase I
What are web services(REST APIs). How to deploy it using docker. What is Docker and containerization? Docker Setup and commands. | Day 1 to Day 9 | Make one backend service with simple get API that returns current date and time. And use docker.yml file to deploy the service | Containerized Backend Service with REST APIs and docker file on GitHub. | 18 | 1. System (Laptop or Desktop) and Internet 2. OS (Windows or macOS) 3. HTTP REST APIS awareness (GET/POST) 4. One Technology stack of choice(node ,Java, C/C++, python) and system setup for creating REST APIs 5. Any IDE for development 6. Docker setup | COMPLETED | 29-05-2023
Containerize and deploy backend with docker yml . Target available code ( Github) which serves business capability (Ex: User Management, Sensor data Visualization ) and How to deploy and check the running instances with Docker and test the REST APIs | Day 10 to Day 15 | .Write yml file to containerize the given backend. Use 'Postman' to test APIs of the running microservices. Upload the code and YML file on your GitHub account. |  | 12 | 1. GitHub Account with knowhow on code push/pull 2. Postman setup and use. 3. Use of available Github Source code for backend service | COMPLETED | 2023-05-19
Phase II
Make Web application for Frontend, UI Development + Navigation | Day 16- Day28 | Create application with 2 Tabs (i) Tab-1 will show the details of currect running docker instances logs with way to start/stop the docker. | A web application showing:- a) details and status of backend docker instance . Can start/stop the instances through this application. b) Data visualization from the service running on docker | 24 | 1. One Technology stack of choice for UI development 2. System setup for developing application | COMPLETED | 2023-06-26
API Integration, Data Parsing, Data visuliazation on sensor screen | Day 29- Day 39 | (ii) Tab-2 Visualize the data received from backend |  | 18
Phase III
Rebuild with new approach -GPT 4 | Day 40- Day 45 | Attempt phase 1 leveraging GPT4 Build docker file using GPT 4 for the backend service created in phase I. Containerized the backend with the created docker file and test the application Use GPT4 approach to containerize the webapplication in Phase 2 from the git repository | Containerization of Web application. Report on the analysis of efforts spent between GPT4 approach and ealier (Phase I) | 6 | GPT4 Free Account
|  | Total Efforts in Person-hours |  | 78

## Queries
Day/Date | Queries | Added by | Status